## Gantt Chart
Kamila Maciejczak
Python Project - Project&Prototyping |  |  | DURATION (days)
START DATE | END DATE | DESCRIPTION
2021-05-05 | 2021-05-06 | Description fo the project design | 1
2021-05-06 | 2021-05-09 | Wireframe code of the project and project design | 3
2021-05-09 | 2021-05-14 | Project coding - creating variables and functions | 5
2021-05-14 | 2021-05-20 | Project coding - creating loops | 6
2021-05-20 | 2021-05-21 | Comments to the code | 1
2021-05-21 | 2021-05-27 | Working at the documentation - development log, resources | 6
2021-05-27 | 2021-05-29 | Project refinement, debuging, testing program | 2
2021-05-29 | 2021-05-30 | Project evaluation | 1
2021-05-30 | 2021-05-31 | Finishing project | 1